{"text_format":"1","workbook":"xlsx","n_sheets":32,"sheets":["Login","InfoConfig","Read Me","Create Release","Create Track","Tracks","All Releases","Release","Tokens","Phases","Add To Track","Create Phase","Tasks","Track Inputs","Track Progress","Create Task","MileStones","MileStones Inputs","MileStones Progress","Release MileStones Progress","User Groups","Applications","Release MileStones Inputs ","MembersParties","OwnerParties","Reports","Activities","Update","Release Inputs","Release Progress","PivotTable","PivotChart"],"not_rendered":{"charts":23,"images":3,"macros":1,"external_links":0,"defined_names":4,"comments":0,"pivot_tables":19},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Login","index":0,"n_rows":18,"n_cols":3,"rows_kept":18,"cut":false,"hidden":false,"merged":[]}
[]
[null,"Continuous Delivery Director"]
[]
[null,"URL","https://cddirector.io/"]
[null,"Authorization Type","Bearer Token"]
[null,"API Key"]
[null,"Tenant ID"]
[]
[null,"Action","Create Release"]
[null,"Free Text(optional)",""]
[null,"Page Size"]
[]
[]
[]
[]
[]
[]
[null,null,"  "]

{"sheet":"InfoConfig","index":1,"n_rows":2,"n_cols":5,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Url","Username","Password","API Key","Tenant ID"]
["https://cddirector.io/","pmutadak@anisolutions.com","P@ssword9","eyJhbGciOiJIUzUxMiJ9.eyJ1c2VybmFtZSI6ImhhcmlzaC5wYXRpbEB0aGlua2l0aXZlLmNvbSIsInRlbmFudElkIjoiNjkzMjkwZDctZWJkZS00NTM4LWE5NzItMjAyYjg2ODMxNDc5IiwidXNlcklkIjoxLCJqdGkiOiJmYTY0ZmYzMy1mODdjLTQ2NDktYTk0OC0zNTk2MjYyNzM5Y2IiLCJleHAiOjE1ODY3Nzg5ODl9.NSPX15x8OPk-eBsIlD3KUae_nOkpyLB0URzbCdvQ7N16zIb8D5SIeRKrHG3fOSOIRE2kJ04LBO_gjctRDN6qCg","693290d7-ebde-4538-a972-202b86831479"]

{"sheet":"Read Me","index":2,"n_rows":63,"n_cols":8,"rows_kept":63,"cut":false,"hidden":false,"merged":[[5,7,5,12],[7,7,7,12],[2,5,4,6],[5,5,7,6],[2,1,5,1],[54,1,62,1],[6,1,9,1],[38,1,44,1],[31,1,37,1],[45,1,53,1],[22,1,30,1],[10,1,15,1],[16,1,21,1]]}
[null,null,null,"Steps How To Use CDD Excel Tool"]
[]
[null,"Get Release","Step 1 :","Goto Login Tab",null,"DateTime Format",null,"It should be \"dd-mm-yy hh:mm\""]
[null,null,"Step 2 :","Select Get Release From Action Drop Down List",null,null,null,"Its automatically convert into above format while typing or"]
[null,null,"Step 3 :","Enter Release Id as Number",null,null,null,"copying."]
[null,null,"Step 4:","Click on Submit",null,"Copy Paste Date",null,"1. Copy date and paste into particular cell"]
[null,"Get Track","Step 1 :","Goto Login Tab",null,null,null,"2. Enter space into cell"]
[null,null,"Step 2 :","Select Get Track From Action Drop Down List",null,null,null,"3. Copy time and paste"]
[null,null,"Step 3 :","Enter Track Id as Number"]
[null,null,"Step 4:","Click on Submit"]
[null,"Create Release","Step 1 :","Goto Login Tab"]
[null,null,"Step 2 :","Select Create Release From Action Drop Down List"]
[null,null,"Step 3:","Click on Submit"]
[null,null,"Step 4:","Goto Create Release Tab"]
[null,null,"Step 5:","Enter Release Details Like Name, Version ,Application, Description etc. "]
[null,null,"Step 6:","Click on Add Release"]
[null,"Create Track","Step 1 :","Goto Login Tab"]
[null,null,"Step 2 :","Select Create Track From Action Drop Down List"]
[null,null,"Step 3:","Click on Submit"]
[null,null,"Step 4:","Goto Create Track Tab"]
[null,null,"Step 5:","Enter Track Details Like Name, Description Prod start date ,Prod end date,Owners etc. "]
[null,null,"Step 6:","Click on Add Track"]
[null,"Add To Track","Step 1 :","Goto Login Tab"]
[null,null,"Step 2 :","Select Get Release From Action Drop Down List"]
[null,null,"Step 3:","Enter Release Id as Number"]
[null,null,"Step 4:","Click on Submit"]
[null,null,"Step 5:","Goto Add To Track Tab"]
[null,null,"Step 6:","Enter Track Id"]
[null,null,"Step 7:","Click on Get Track"]
[null,null,"Step 8:","Select Phases only"]
[null,null,"Step 9:","Click on Add To Track Button"]
[null,"Create Task","Step 1 :","Goto Login Tab"]
[null,null,"Step 2 :","Select Get Release From Action Drop Down List"]
[null,null,"Step 3 :","Enter Release Id as Number"]
[null,null,"Step 4:","Click on Submit"]
[null,null,"Step 5:","Goto Create Task Tab"]
[null,null,"Step 6:","Enter Task Details Like Phase Id ,Name etc. (if you don’t know phase Id Please copy phase Id from Phases and Tasks Tab)"]
[null,null,"Step 7:","Click on Add Task"]
[null,"Create Phase","Step 1 :","Goto Login Tab"]
[null,null,"Step 2 :","Select Get Release From Action Drop Down List"]
[null,null,"Step 3 :","Enter Release Id as Number"]
[null,null,"Step 4:","Click on Submit"]
[null,null,"Step 5:","Goto Create Phase Tab"]
[null,null,"Step 6:","Enter Phase Details Like Phase Name, Description,Approval Gate,Schedule Dates, Owners etc. (Note:Schedule Start Date and Schedule End Date are madnatory when Approval Gate Value is 'SCHEDULED'.And Date Format Should be system Date format.)"]
[null,null,"Step 7:","Click on Add Phase"]
[null,"Update Tasks","Step 1 :","Goto Login Tab"]
[null,null,"Step 2 :","Select Get Release From Action Drop Down List"]
[null,null,"Step 3 :","Enter Release Id as Number"]
[null,null,"Step 4:","Click on Submit"]
[null,null,"Step 5:","Goto Tasks Tab"]
[null,null,"Step 6:","Edit Task Details Like Task Name,Task Description,Rating,Comment,Schedule Dates etc."]
[null,null,"Step 7:","Goto Login Tab"]
[null,null,"Step 8:","Select Update Tasks From Action Drop Down List"]
[null,null,"Step 7:","Click on Submit"]
[null,"Update Phases","Step 1 :","Goto Login Tab"]
[null,null,"Step 2 :","Select Get Release From Action Drop Down List"]
[null,null,"Step 3 :","Enter Release Id as Number"]
[null,null,"Step 4:","Click on Submit"]
[null,null,"Step 5:","Goto Phases Tab"]
[null,null,"Step 6:","Edit Phase Details Like Name,Description,Approval Gate,Owners,Schedule Dates etc.(Note:Schedule Start Date and Schedule End Date are madnatory when Approval Gate Value is 'SCHEDULED'.)"]
[null,null,"Step 7:","Goto Login Tab"]
[null,null,"Step 8:","Select Update Phases From Action Drop Down List"]
[null,null,"Step 7:","Click on Submit"]

{"sheet":"Create Release","index":3,"n_rows":4,"n_cols":6,"rows_kept":4,"cut":false,"hidden":true,"merged":[]}
[]
[]
[]
["Name *","Version *","Description","Applications *","Owners","Members"]

{"sheet":"Create Track","index":4,"n_rows":4,"n_cols":25,"rows_kept":4,"cut":false,"hidden":true,"merged":[[1,2,1,6]]}
[]
[]
[]
["Name *","Description ","Production Start Date *","Production End Date *","Owners","Milestone Name1","Milestone Due Date1","Milestone Name2","Milestone Due Date2","Milestone Name3","Milestone Due Date3","Milestone Name4","Milestone Due Date4","Milestone Name5","Milestone Due Date5","Milestone Name6","Milestone Due Date6","Milestone Name7","Milestone Due Date7","Milestone Name8","Milestone Due Date8","Milestone Name9","Milestone Due Date9","Milestone Name10","Milestone Due Date10"]

{"sheet":"Tracks","index":5,"n_rows":9,"n_cols":9,"rows_kept":9,"cut":false,"hidden":true,"merged":[]}
["ID","Name","Creation Date","Start Date","End Date","Status","Milestone Id","Milestone Name","Due Date"]
[1,"Special Olympics Athlete Management System","2017-08-22T22:42:14","2017-09-16T08:40:30","2017-09-17T20:29:30","DONE",4,"Testing and Staging Completed","2017-09-16T07:20:00"]
[1,"Special Olympics Athlete Management System","2017-08-22T22:42:14","2017-09-16T08:40:30","2017-09-17T20:29:30","DONE",5,"Development Work Completed","2017-09-10T08:30:00"]
[]
[2,"SunLife Testing","2019-03-11T21:25:32","2019-03-12T21:25:11","2019-03-13T22:25:11","DONE"]
[3,"Wellesley Milestones DR Exercise Track","2019-04-25T09:51:38","2019-04-27T09:51:26","2019-04-30T12:14:21","DONE"]
[4,"Test for upgrade CDD","2019-04-25T12:25:55","2019-04-29T12:25:06","2019-04-30T13:25:06","DONE"]
[6,"Test Track","2019-05-21T12:33:38","2019-05-22T12:33:28","2019-05-23T13:33:28","DONE"]
[9,"Test CDA Plugin","2019-05-30T13:51:07","2019-05-31T13:50:48","2019-06-02T14:50:48","DONE"]

{"sheet":"All Releases","index":6,"n_rows":51,"n_cols":12,"rows_kept":51,"cut":false,"hidden":true,"merged":[]}
["Id","Name","Version","Status","Description","Owners","App Id","Application","Creation Date","Start Date","Source Name","Delatable"]
[723,"BeanLogin Release - PROD 03192019",1,"RUNNING_WITH_ERRORS",3192019,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-19T06:48:25","2019-03-19T06:48:43","CARA Endpoint",false]
[722,"BeanLogin Release - QA - 03152018B",2,"RUNNING","BeanLogin Release - QA -03152018B","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-15T11:40:19","2019-03-15T11:40:46","CARA Endpoint",false]
[721,"BeanLogin Release - QA - 03152018A",2,"DESIGN","BeanLogin Release - QA -03152018A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-15T11:14:53",null,"CARA Endpoint",false]
[720,"BeanLogin Release - PROD 03152019",1,"RUNNING_WITH_ERRORS",3152019,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-15T10:32:30","2019-03-15T10:33:32","CARA Endpoint",false]
[719,"BeanLogin Release - PROD 03142019",1,"DONE",3142019,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-14T11:08:57","2019-03-14T11:09:15","CARA Endpoint",false]
[718,"Wellesley DR Exercise Release - Sunlife",1,"DESIGN",null,"EI - Systems Management , pmutadak@anisolutions.com , AS-AOS-Image and Workflow",67,"BeanLogin","2019-03-12T09:29:03",null,"CARA Endpoint",false]
[717,"Wellesley DR Exercise Release",1,"DONE",null,"pmutadak@anisolutions.com",67,"BeanLogin","2019-03-12T06:43:56","2019-03-12T06:46:12","CARA Endpoint",false]
[716,"BeanLogin Release - PROD 03082019A",1,"RUNNING","03082019A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-08T13:22:42","2019-03-08T13:25:15","CARA Endpoint",false]
[715,"BeanLogin Release - PROD 03072019C",1,"DONE","03072019C","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-07T13:17:36","2019-03-07T13:17:49","CARA Endpoint",false]
[714,"BeanLogin Release - PROD 03072019B",1,"DONE","03072019B","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-07T09:29:24","2019-03-07T09:29:42","CARA Endpoint",false]
[713,"BeanLogin Release - PROD 03072019A",1,"RUNNING","03072019A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-07T09:00:19","2019-03-07T09:00:56","CARA Endpoint",false]
[712,"BeanLogin Release - PROD 03052019A",1,"DONE","03052019A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-05T13:09:14","2019-03-05T13:10:54","CARA Endpoint",false]
[711,"Wellesley Milestones DR Exercise Harish",2,"DESIGN","Wellesley DR ExerciseThis is the release specifically made for simulations:* Only DR teams members are owners (Steve/Trevor)* Only DR team members have been assigned tasks* The amount of phases and tasks have been reduced to compensate for time","jbalsavage@anisolutions.com , pmutadak@anisolutions.com",72,"Ansible DR","2019-03-05T05:38:34",null,"Local",true]
[710,"Wellesley Milestones DR Exercise - DTE DEMO2 - Copy","2019_DRY-RUN_01","DONE","Wellesley DR ExerciseThis is the release specifically made for simulations:* Only DR teams members are owners (Steve/Trevor)* Only DR team members have been assigned tasks* The amount of phases and tasks have been reduced to compensate for time","jbalsavage@anisolutions.com",72,"Ansible DR","2019-03-05T05:33:54","2019-03-05T05:34:22","Local",true]
[709,"BeanLogin Release - QA -  03042019A",2,"DESIGN","BeanLogin Release - QA -03042019A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-04T08:00:06",null,"CARA Endpoint",false]
[708,"BeanLogin Release - QA -  03042019",2,"DESIGN","BeanLogin Release - QA -03042019","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-04T07:57:10",null,"CARA Endpoint",false]
[707,"Wellesley Milestones DR Exercise - DTE DEMO2","2019_DRY-RUN_01","DESIGN","Wellesley DR ExerciseThis is the release specifically made for simulations:* Only DR teams members are owners (Steve/Trevor)* Only DR team members have been assigned tasks* The amount of phases and tasks have been reduced to compensate for time","jbalsavage@anisolutions.com",72,"Ansible DR","2019-03-01T18:48:00",null,"Local",true]
[706,"BeanLogin Release - PROD 01032019B",1,"DONE","01032019B","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-01T09:49:50","2019-03-01T09:50:07","CARA Endpoint",false]
[705,"BeanLogin Release - PROD 01032019A",1,"DONE","01032019A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-03-01T09:10:36","2019-03-01T09:11:02","CARA Endpoint",false]
[704,"BeanLogin Release - QA -  02282019",2,"DONE","BeanLogin Release - QA -02282019","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-28T15:09:01","2019-02-28T15:09:21","CARA Endpoint",false]
[703,"Wellesley Milestones DR Exercise - DTE DEMO","2019_DRY-RUN_01","DONE","Wellesley DR ExerciseThis is the release specifically made for simulations:* Only DR teams members are owners (Steve/Trevor)* Only DR team members have been assigned tasks* The amount of phases and tasks have been reduced to compensate for time","jbalsavage@anisolutions.com",72,"Ansible DR","2019-02-28T03:44:03","2019-03-01T18:25:58","Local",true]
[702,"BeanLogin Release - PROD 02272019B",1,"DONE","02272019B","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-27T13:10:38","2019-02-27T13:10:53","CARA Endpoint",false]
[701,"BeanLogin Release - PROD 02272019",1,"DONE",2272019,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-27T07:07:56","2019-02-27T07:08:19","CARA Endpoint",false]
[700,"BeanLogin Release - PROD 02262019CC",1,"DONE","02262019CC","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-26T14:30:29","2019-02-26T14:30:50","CARA Endpoint",false]
[699,"BeanLogin Release - PROD 02262018BB",1,"DONE","02262018BB","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-26T14:09:11","2019-02-26T14:09:24","CARA Endpoint",false]
[698,"BeanLogin Release - PROD 02262019A",1,"DONE","02262019A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-26T13:24:25","2019-02-26T13:25:17","CARA Endpoint",false]
[697,"BeanLogin Release - QA -  02252019AA",2,"DONE","BeanLogin Release - QA -02252019AA&#xfeff;","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-25T14:56:50","2019-02-25T14:57:05","CARA Endpoint",false]
[696,"BeanLogin Release - PROD 02252018A",1,"DONE","02252018A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-25T13:46:16","2019-02-25T13:46:44","CARA Endpoint",false]
[695,"BeanLogin Release - PROD 02252018",1,"DONE",2252018,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-25T11:55:19","2019-02-25T11:55:41","CARA Endpoint",false]
[694,"BeanLogin Release - PROD 02222018A",1,"DONE","02222018A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-22T14:10:02","2019-02-22T14:12:46","CARA Endpoint",false]
[693,"BeanLogin Release - PROD 02222018",1,"DONE",2222018,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-22T10:06:06","2019-02-22T10:06:30","CARA Endpoint",false]
[692,"BeanLogin Release - PROD 02212018",1,"DONE",2212018,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-21T15:35:31","2019-02-21T15:35:59","CARA Endpoint",false]
[691,"BeanLogin Release - PROD 02202018C",1,"DONE","02202018BC","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-20T12:08:32","2019-02-20T12:09:33","CARA Endpoint",false]
[690,"BeanLogin Release - PROD 02202018B",1,"DONE","02202018B&#xfeff;","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-20T07:39:45","2019-02-20T07:40:02","CARA Endpoint",false]
[689,"BeanLogin Release - PROD 02202018A",1,"DONE","02202018A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-20T07:02:53","2019-02-20T07:03:43","CARA Endpoint",false]
[688,"BeanLogin Release - PROD 02192018CC",1,"DONE","02192018CC","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T14:21:39","2019-02-19T14:21:51","CARA Endpoint",false]
[687,"BeanLogin Release - PROD 02192018BB",1,"DONE","02192018BB","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T14:10:41","2019-02-19T14:10:56","CARA Endpoint",false]
[685,"BeanLogin Release - QA -  02192019F",2,"DONE","BeanLogin Release - QA - 02192019F","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T12:26:42","2019-02-19T12:26:55","CARA Endpoint",false]
[684,"BeanLogin Release - QA -  02192019E",2,"DONE","BeanLogin Release - QA - 02192019E","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T12:23:06","2019-02-19T12:23:18","CARA Endpoint",false]
[683,"BeanLogin Release - QA -  02192019D",2,"DONE","BeanLogin Release - QA - 02192019D","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T11:36:36","2019-02-19T11:36:59","CARA Endpoint",false]
[682,"BeanLogin Release - QA -  02192019C",2,"DONE","BeanLogin Release - QA - 02192019","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T11:32:40","2019-02-19T11:32:54","CARA Endpoint",false]
[681,"BeanLogin Release - QA -  02192019B",2,"DONE","BeanLogin Release - QA - 02192019","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T11:02:06","2019-02-19T11:02:31","CARA Endpoint",false]
[680,"BeanLogin Release - PROD 02192018A",1,"DONE","02192018A","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T09:25:00","2019-02-19T09:41:17","CARA Endpoint",false]
[679,"BeanLogin Release - QA -  02192018",2,"DONE","BeanLogin Release - QA - 02192018","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-19T08:19:03","2019-02-19T08:19:23","CARA Endpoint",false]
[678,"BeanLogin Release - PROD 02182019B",1,"DONE","02182019B","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-18T14:33:31","2019-02-18T14:33:45","CARA Endpoint",false]
[677,"BeanLogin Release - QA -  02182018",2,"DONE","BeanLogin Release - QA - 02182018","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-18T14:24:18","2019-02-18T14:24:30","CARA Endpoint",false]
[676,"BeanLogin Release - PROD 02182019",1,"DONE",2182019,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-18T12:08:51","2019-02-18T12:09:11","CARA Endpoint",false]
[675,"BeanLogin Release - PROD 02152019",1,"DONE",2152019,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-15T11:36:28","2019-02-15T11:36:53","CARA Endpoint",false]
[674,"BeanLogin Release - QA -  02152018",2,"DONE","BeanLogin Release - QA - 02152018","jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-15T05:35:20","2019-02-15T05:35:37","CARA Endpoint",false]
[673,"BeanLogin Release - PROD 02142019",1,"DONE",2142019,"jbalsavage@anisolutions.com , rgreen@anisolutions.com , thiggins@anisolutions.com , gvarahade@anisolutions.com",67,"BeanLogin","2019-02-14T06:53:24","2019-02-14T06:53:44","CARA Endpoint",false]

{"sheet":"Release","index":7,"n_rows":2,"n_cols":13,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Id","Name","Version","Status","Description","Owners","Members","App Id","Application","Creation Date","Start Date","Source Name","Delatable"]
[18,"Test Time Issue",1,"DESIGN",null,null,null,"3","CDD Upgrade","2020-02-03T17:32:26",null,"Local","True"]

{"sheet":"Tokens","index":8,"n_rows":2,"n_cols":4,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["ID","Name","Value","Scope"]
[19,"CDD Upgrade.last_successful_change",null,"PHASE_SCOPE"]

{"sheet":"Phases","index":9,"n_rows":56,"n_cols":22,"rows_kept":56,"cut":false,"hidden":true,"merged":[]}
["Track Name","Track Status","Release Id","Release Name","Release Version","Phase Id","Phase Name","Phase Status","Phase Percentage Completed","Phase Description","Phase Approval Gate","Phase Sched Start Date","Phase Sched End Date","Phase Owner","Phase Start Date","Phase End Date","Phase Is Production","Phase Is Need Approval","Phase Is Disabled","Phase Deny/Approve Reason","Phase Revision","Phase Allowed Statuses"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,1,"Phase 1.1","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-01-15T19:21:03","2020-01-15T20:21:03","harish.patil@thinkitive.com",null,null,true,false,false,"TRANSITION_DOES_NOT_EXIST",46]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,2,"Phase 2.1","DONE",null,"Test By Harish","SCHEDULED","2020-01-15T19:21:03","2020-01-15T20:21:03","harish.patil@thinkitive.com","2020-01-31T17:28:50","2020-01-31T17:31:19",false,false,false,"TRANSITION_DOES_NOT_EXIST",61,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,3,"Phase 3.1","DONE",null,"","MANUAL",null,null,"harish.patil@thinkitive.com","2020-01-31T17:31:33","2020-01-31T17:32:03",false,false,false,"TRANSITION_DOES_NOT_EXIST",64,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,4,"Testing","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",55,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,10,"Test","DESIGN",null,"","SCHEDULED","2020-03-15T19:21:03","2020-03-15T20:21:03","harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",55,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,14,"Phase1","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",55,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,17,"Phase123","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",55,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,18,"Phase124","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",55,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,29,"Tes12345","DESIGN",null,"","SCHEDULED","2020-04-15T19:21:03","2020-04-15T20:21:03","harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",54,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,30,"Tes12346","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",54,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,31,"Tes12347","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",54,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,32,"Tes12348","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",54,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,33,"Tes12349","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",54,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,34,"Tes12350","DESIGN",null,"updated by Harish","SCHEDULED","2020-02-15T19:21:03","2020-02-15T20:21:03","harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",50,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,35,"Tes12351","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,36,"Tes12352","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,37,"Tes12353","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,38,"Tes12354","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,39,"Tes12355","DESIGN",null,"","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,40,"Test123","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,"harish.patil@thinkitive.com",null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,41,"Test124","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,42,"Test125","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,43,"Test126","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,44,"Test127","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,45,"Test128","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,46,"Test129","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,47,"Test130","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,48,"Test131","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,49,"Test132","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,50,"Test133","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",53,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,51,"Test134","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",50,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,190,"111","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-06-25T11:00:00","2020-06-26T11:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",17,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,191,"112","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,192,"113","DESIGN",null,"Test By Harish Patil","AUTOMATIC",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,193,"114","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-07-25T11:00:00","2020-08-25T11:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,194,"115","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,195,"116","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,196,"117","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-05-25T11:00:00","2020-05-27T11:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,197,"118","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,198,"119","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,199,"120","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-04-25T11:00:00","2020-04-25T11:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,200,"121","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,201,"122","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,202,"123","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,203,"124","DESIGN",null,"Test By Harish Patil","AUTOMATIC",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,204,"125","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,205,"126","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,206,"127","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-03-25T11:00:00","2020-03-26T11:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,207,"128","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,208,"129","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,209,"130","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-03-25T11:00:00","2020-05-25T11:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,210,"131","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-03-26T11:00:00","2020-05-26T11:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,211,"132","DESIGN",null,"Test By Harish Patil","MANUAL",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,212,"133","DESIGN",null,"Test By Harish Patil","AUTOMATIC",null,null,null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",21,"RUNNING"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,213,"134","DESIGN",null,"Test By Harish Patil","SCHEDULED","2020-02-23T12:00:00","2020-02-24T12:00:00",null,null,null,false,false,false,"TRANSITION_DOES_NOT_EXIST",20,"RUNNING"]

{"sheet":"Add To Track","index":10,"n_rows":7,"n_cols":5,"rows_kept":7,"cut":false,"hidden":true,"merged":[[2,4,2,11]]}
[]
[null,"Track ID:"]
[null,null,null,null,"Note: First get track data then select phases only and click on Add to track"]
[]
[]
[]
["Milestones Ids","Milestones/Production Phase","Select Phases","Start Date","End Date"]

{"sheet":"Create Phase","index":11,"n_rows":4,"n_cols":6,"rows_kept":4,"cut":false,"hidden":true,"merged":[[1,1,1,5]]}
[]
[null,"Note:Schedule Start Date and Schedule End Date are madnatory when Approval Gate Value is 'SCHEDULED'."]
[]
["Name(*)","Approval Gate","Sched Start Date","Sched End Date","Owners","Description"]

{"sheet":"Tasks","index":12,"n_rows":67,"n_cols":31,"rows_kept":67,"cut":false,"hidden":true,"merged":[]}
["Track Name","Track Status","Release Id","Release Name","Release Version","MSID","Phase Name","Phase Status","Task Name","Task Status","Task Owners","Task Description","Task Rating","Task Comment","Task Owner Contact","Task Predecessor Id","Task Sched Start Time","Task Sched End Time","Task Duration","Task Start Date","Task End Date","Task EndPoint","Phase Id","Task Id","Prev Tasks","Next Tasks","Task Is Disabled","Task Percentage Completed","Task Allowed Statuses","Task Deny/Rerun Reason","Task Revision"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test 1.5","DESIGN","harish.patil@thinkitive.com","Test 1.1","1","Task updated By John","362374348","1","2020-01-11","2020-01-15",4,null,null,null,1,1,null,"12",false,null,null,"TRANSITION_DOES_NOT_EXIST",15]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,9,null,"12",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,10,null,"12",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,11,null,"12",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test1235e65","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,14,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test1235e66","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,15,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","HarishTest","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,16,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","HarishTest2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,17,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","NewTask","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,18,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","NewTask2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,19,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","TestNewTask","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,20,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","TestNewTask2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,21,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test12378678","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,22,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test12378679","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,23,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","Test123","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,12,"1 , 9 , 10 , 11","13",false,null,null,"TRANSITION_DOES_NOT_EXIST",1]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 1.1","DESIGN","dsfsdf23","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,1,13,"12",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",1]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,11,"Phase 2.1","DONE","11 - Test 1.6","DONE","harish.patil@thinkitive.com","1- Test 1.2 ","2","Test Task Update","362374349","5","2020-01-12","2020-01-16",4,"2020-01-31T17:30:58","2020-01-31T17:30:58",null,2,2,null,"3",false,100,null,"TRANSITION_DOES_NOT_EXIST",16]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,12,"Phase 2.1","DONE","12 - Test 1.7","DONE","harish.patil@thinkitive.com","2-Test 1.3","6","","","",null,null,0,"2020-01-31T17:31:02","2020-01-31T17:31:02",null,2,6,null,"3",false,100,null,"TRANSITION_DOES_NOT_EXIST",13]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 2.1","DONE","Testing","DONE",null,"",null,null,null,null,null,null,null,"2020-01-31T17:31:09","2020-01-31T17:31:09",null,2,7,null,null,false,100,null,"TRANSITION_DOES_NOT_EXIST",3]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 2.1","DONE","NewTaskHarish","DONE",null,"",null,null,null,null,null,null,null,"2020-01-31T17:31:14","2020-01-31T17:31:14",null,2,24,null,null,false,100,null,"TRANSITION_DOES_NOT_EXIST",3]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 2.1","DONE","NewTaskHarish2","DONE",null,"",null,null,null,null,null,null,null,"2020-01-31T17:31:06","2020-01-31T17:31:06",null,2,27,null,null,false,100,null,"TRANSITION_DOES_NOT_EXIST",3]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 2.1","DONE","Test@123","DONE","harish.patil@thinkitive.com","Test 1.4","3","","","",null,null,0,"2020-01-31T17:31:19","2020-01-31T17:31:19",null,2,3,"6 , 2",null,false,100,null,"TRANSITION_DOES_NOT_EXIST",13]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 3.1","DONE","Test 1.9","DONE","harish.patil@thinkitive.com","Test 1.5","5","","","",null,null,0,"2020-01-31T17:31:38","2020-01-31T17:31:38",null,3,5,null,"4",false,100,null,"TRANSITION_DOES_NOT_EXIST",10]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 3.1","DONE","Testmm","DONE",null,"",null,null,null,null,null,null,null,"2020-01-31T17:31:42","2020-01-31T17:31:42",null,3,8,null,null,false,100,null,"TRANSITION_DOES_NOT_EXIST",3]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 3.1","DONE","Test1","DONE",null,"",null,null,null,null,null,null,null,"2020-01-31T17:31:46","2020-01-31T17:31:46",null,3,29,null,null,false,100,null,"TRANSITION_DOES_NOT_EXIST",3]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 3.1","DONE","Test2","DONE",null,"",null,null,null,null,null,null,null,"2020-01-31T17:31:50","2020-01-31T17:31:50",null,3,32,null,null,false,100,null,"TRANSITION_DOES_NOT_EXIST",3]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase 3.1","DONE","Test 1.10","DONE","harish.patil@thinkitive.com","Test 1.6","4","","","",null,null,0,"2020-01-31T17:32:03","2020-01-31T17:32:03",null,3,4,"5",null,false,100,null,"TRANSITION_DOES_NOT_EXIST",21]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Testing","DESIGN","sdhjsdfjsdjfjf","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,4,34,null,"35",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Testing","DESIGN","Testing123","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,4,37,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Testing","DESIGN","Testing124","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,4,41,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Testing","DESIGN","Testing125","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,4,44,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Testing","DESIGN","sdhjsdfjsdjfjf2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,4,35,"34","36",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Testing","DESIGN","sdhjsdfjsdjfjf5","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,4,36,"35",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing123","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,46,null,"47",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing123456789","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,50,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing-Dev1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,54,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing-Dev2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,58,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing-Dev4","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,60,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing124","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,47,"46","48",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing125","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,48,"47","49",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Test","DESIGN","Testing126","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,10,49,"48",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase1","DESIGN","HarishTask1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,14,61,null,"62",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase1","DESIGN","HarishPhaseTask1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,14,64,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase1","DESIGN","HarishPhaseTask3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,14,66,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase1","DESIGN","HarishTask2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,14,62,"61","63",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase1","DESIGN","HarishTask3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,14,63,"62",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase123","DESIGN","TaskTest1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,17,67,null,"68",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase123","DESIGN","NameTask1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,17,70,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase123","DESIGN","NameTask3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,17,72,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase123","DESIGN","TaskTest2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,17,68,"67","69",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase123","DESIGN","TaskTest3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,17,69,"68",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase124","DESIGN","Test1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,18,73,null,"74",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase124","DESIGN","Test3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,18,75,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Phase124","DESIGN","Test2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,18,74,"73",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12345","DESIGN","Testing1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,29,77,null,"78",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12345","DESIGN","Testing99","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,29,80,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12345","DESIGN","App3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,29,87,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12345","DESIGN","App5","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,29,89,null,null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12345","DESIGN","Testing2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,29,78,"77","79",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12345","DESIGN","Testing3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,29,79,"78",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12346","DESIGN","Test1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,30,81,null,"82",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12346","DESIGN","Test2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,30,82,"81","83",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12346","DESIGN","Test3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,30,83,"82","84",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12346","DESIGN","Testing1","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,30,84,"83","85",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12346","DESIGN","Testing2","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,30,85,"84","86",false,null,null,"TRANSITION_DOES_NOT_EXIST",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool",1,null,"Tes12346","DESIGN","Testing3","DESIGN",null,"",null,null,null,null,null,null,null,null,null,null,30,86,"85",null,false,null,null,"TRANSITION_DOES_NOT_EXIST",0]

{"sheet":"Track Inputs","index":13,"n_rows":27,"n_cols":13,"rows_kept":27,"cut":false,"hidden":true,"merged":[]}
[]
["Phase Status","(All)"]
[]
[null,"Column Labels"]
[null,"Phase 1.1","Phase 2.1","Phase 3.1","Phase1","Phase123","Phase124","Tes12345","Tes12346","Test","Testing","(blank)","Grand Total"]
["Count of Phase Status",0.24242424242424243,9.0909090909090912E-2,7.575757575757576E-2,7.575757575757576E-2,7.575757575757576E-2,4.5454545454545456E-2,9.0909090909090912E-2,9.0909090909090912E-2,0.12121212121212122,9.0909090909090912E-2,0,1]
[]
["Track Status","(All)"]
[]
[null,"Column Labels"]
[null,"(blank)","harish.patil@thinkitive.com","Grand Total"]
["Count of Track Status",0.90909090909090906,9.0909090909090912E-2,1]
[]
[]
[]
[]
[null,"NOT_APPROVED","(blank)","Grand Total"]
["Count of Track Status",1,0,1]
[]
[]
[]
[]
["Task Status","(All)"]
[]
[null,"Column Labels"]
[null,"Added From Excel Tool","(blank)","Grand Total"]
["Count of Task Status",1,0,1]

{"sheet":"Track Progress","index":14,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Create Task","index":15,"n_rows":4,"n_cols":10,"rows_kept":4,"cut":false,"hidden":true,"merged":[]}
[]
[]
[]
["Phase ID(*)","Name(*)","Description","Rating","Comment","Owner Contact","Predecessor Id","Sched Start Time","Sched End Time","Owners"]

{"sheet":"MileStones","index":16,"n_rows":67,"n_cols":25,"rows_kept":67,"cut":false,"hidden":true,"merged":[]}
["Track Name","Track Status","Release Id","Release Name","Phase","Team Name","MSID","Status","Task Description","Planned Start","Planned Finish","Planned Duration","Actual Start","Actual Finish","Actual Duration","Dependency 1","Dependency 2","Dependency 3","Dependency 4","Dependency 5","Successor 1","Successor 2","Successor 3","Successor 4","Successor 5"]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1","harish.patil@thinkitive.com",null,"Not Started","Test 1.1","2020-01-11","2020-01-15",4,null,null,0,"1",null,null,null,null,3]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 1.1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 2.1","harish.patil@thinkitive.com",11,"Complete Late"," Test 1.2 ","2020-01-12","2020-01-16",4,"2020-01-31T17:30:58","2020-01-31T17:30:58",0,"5",null,null,null,null,7]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 2.1","harish.patil@thinkitive.com",12,"DONE","Test 1.3",null,null,0,"2020-01-31T17:31:02","2020-01-31T17:31:02",0,""]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 2.1",null,null,"DONE",null,null,null,0,"2020-01-31T17:31:09","2020-01-31T17:31:09",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 2.1",null,null,"DONE",null,null,null,0,"2020-01-31T17:31:14","2020-01-31T17:31:14",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 2.1",null,null,"DONE",null,null,null,0,"2020-01-31T17:31:06","2020-01-31T17:31:06",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 2.1","harish.patil@thinkitive.com",null,"DONE","Test 1.4",null,null,0,"2020-01-31T17:31:19","2020-01-31T17:31:19",0,""]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 3.1","harish.patil@thinkitive.com",null,"DONE","Test 1.5",null,null,0,"2020-01-31T17:31:38","2020-01-31T17:31:38",0,""]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 3.1",null,null,"DONE",null,null,null,0,"2020-01-31T17:31:42","2020-01-31T17:31:42",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 3.1",null,null,"DONE",null,null,null,0,"2020-01-31T17:31:46","2020-01-31T17:31:46",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 3.1",null,null,"DONE",null,null,null,0,"2020-01-31T17:31:50","2020-01-31T17:31:50",0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase 3.1","harish.patil@thinkitive.com",null,"DONE","Test 1.6",null,null,0,"2020-01-31T17:32:03","2020-01-31T17:32:03",0,""]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Testing",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Testing",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Testing",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Testing",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Testing",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Testing",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Test",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase1",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase123",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase123",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase123",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase123",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase123",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase124",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase124",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Phase124",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12345",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12345",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12345",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12345",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12345",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12345",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12346",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12346",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12346",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12346",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12346",null,null,"Not Started",null,null,null,0,null,null,0]
["Test Track","NOT_APPROVED",1,"Added From Excel Tool","Tes12346",null,null,"Not Started",null,null,null,0,null,null,0]

{"sheet":"MileStones Inputs","index":17,"n_rows":25,"n_cols":7,"rows_kept":25,"cut":false,"hidden":true,"merged":[]}
[null,"Status","(Multiple Items)"]
[]
[null,null,"Column Labels"]
[null,null,"Phase 2.1","Phase 3.1","Grand Total"]
[null,"Count of Status",0.54545454545454541,0.45454545454545453,1]
[]
[]
[]
[]
[null,null,"Column Labels"]
[null,null,"Complete Late","DONE","Not Started","(blank)","Grand Total"]
[null,"Count of Status",1.5151515151515152E-2,0.15151515151515152,0.83333333333333337,0,1]
[]
[]
[null,"Status","(Multiple Items)"]
[]
[null,null,"Column Labels"]
[null,null,"(blank)","harish.patil@thinkitive.com","Grand Total"]
[null,"Count of Status",0.54545454545454541,0.45454545454545453,1]
[]
[null,"Status","(Multiple Items)"]
[]
[null,null,"Column Labels"]
[null,null,"Added From Excel Tool","Grand Total"]
[null,"Count of Status",1,1]

{"sheet":"MileStones Progress","index":18,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Release MileStones Progress","index":19,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"User Groups","index":20,"n_rows":2,"n_cols":3,"rows_kept":2,"cut":false,"hidden":true,"merged":[]}
["Id","Group/User Name","Role"]
[1,"harish.patil@thinkitive.com","Administrator"]

{"sheet":"Applications","index":21,"n_rows":5,"n_cols":2,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["App. Id","App. Name"]
[4,"Application DDL Test1"]
[5,"Application DDL Testing"]
[2,"CDD DR Testing"]
[3,"CDD Upgrade"]

{"sheet":"Release MileStones Inputs ","index":22,"n_rows":19,"n_cols":4,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
[null,"Status","(blank)"]
[]
[null,null,"Column Labels"]
[null,null,"(blank)","Grand Total"]
[null,"Count of Status",{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
[]
[]
[]
[]
[null,null,"Column Labels"]
[null,null,"(blank)","Grand Total"]
[null,"Count of Status",{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
[]
[]
[null,"Status","(Multiple Items)"]
[]
[null,null,"Column Labels"]
[null,null,"Grand Total"]
[null,"Count of Status",{"$error":"#DIV/0!"}]

{"sheet":"MembersParties","index":23,"n_rows":28,"n_cols":9,"rows_kept":28,"cut":false,"hidden":true,"merged":[]}
["Id","First Name","Last Name","Email Address","Is Super User","Role","Class Name","Notification Enabled","Description"]
[5,"John","Balsavage","jbalsavage@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[5,"John","Balsavage","jbalsavage@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[1,"Super","User","superuser@ca.com",true,"SYSTEM_ADMINISTRATOR","UserDto",true]
[2,"Vanessa","Keal","vkeal@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[4,"Chip","Rabinowitz","crabinowitz@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[5,"John","Balsavage","jbalsavage@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[1,"Super","User","superuser@ca.com",true,"SYSTEM_ADMINISTRATOR","UserDto",true]
[2,"Vanessa","Keal","vkeal@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[4,"Chip","Rabinowitz","crabinowitz@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[5,"John","Balsavage","jbalsavage@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true,"Demo Administrator"]
[2,"Vanessa","Keal","vkeal@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true,"Demo Administrator"]
[4,"Chip","Rabinowitz","crabinowitz@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true,"Demo Administrator"]
[32,"John","Balsavage","john@beanlogin.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[5,"John","Balsavage","jbalsavage@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[1,"Super","User","superuser@ca.com",true,"SYSTEM_ADMINISTRATOR","UserDto",true]
[2,"Vanessa","Keal","vkeal@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[4,"Chip","Rabinowitz","crabinowitz@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[25,"Pooja","Mutadak","pmutadak@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[5,"John","Balsavage","jbalsavage@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true,"This team performs final testing and staging of the software in preparation for it going into Production"]
[1,"Super","User","superuser@ca.com",true,"SYSTEM_ADMINISTRATOR","UserDto",true,"This team performs final testing and staging of the software in preparation for it going into Production"]
[2,"Vanessa","Keal","vkeal@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true,"This team performs final testing and staging of the software in preparation for it going into Production"]
[4,"Chip","Rabinowitz","crabinowitz@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true,"This team performs final testing and staging of the software in preparation for it going into Production"]
[30,"Daniel","Dunn","ddunn@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[28,"Sesha","Palakodety","spalakodety@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[1,"Super","User","superuser@ca.com",true,"SYSTEM_ADMINISTRATOR","UserDto",true]
[2,"Vanessa","Keal","vkeal@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[33,"sso","sso","sso@sso.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]

{"sheet":"OwnerParties","index":24,"n_rows":7,"n_cols":9,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
["Id","Track ID","First Name","Last Name","Email Address","Is Super User","Role","Class Name","Notification Enabled"]
[1,1,"Super","User","superuser@ca.com",true,"SYSTEM_ADMINISTRATOR","UserDto",true]
[28,2,"Sesha","Palakodety","spalakodety@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[5,3,"John","Balsavage","jbalsavage@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[25,4,"Pooja","Mutadak","pmutadak@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[25,6,"Pooja","Mutadak","pmutadak@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]
[25,9,"Pooja","Mutadak","pmutadak@anisolutions.com",false,"SYSTEM_ADMINISTRATOR","UserDto",true]

{"sheet":"Reports","index":25,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Activities","index":26,"n_rows":8,"n_cols":11,"rows_kept":8,"cut":false,"hidden":true,"merged":[]}
["ID","Activity Type","Creation Date","Task ID","Phase ID","Release ID","Activity Class","Status","Content Template","Content Class","Content Values"]
[392,"INFO","2020-02-03T17:44:17",null,189,18,"ActivityDto","FINAL","phaseCreated",null,"p00"]
[391,"INFO","2020-02-03T17:43:01",null,188,18,"ActivityDto","FINAL","phaseCreated",null,"p00"]
[390,"INFO","2020-02-03T17:36:54",null,187,18,"ActivityDto","FINAL","phaseCreated",null,"p00"]
[389,"INFO","2020-02-03T17:35:27",null,186,18,"ActivityDto","FINAL","phaseCreated",null,"p00"]
[388,"INFO","2020-02-03T17:35:26",null,185,18,"ActivityDto","FINAL","phaseCreated",null,"p00"]
[387,"INFO","2020-02-03T17:32:26",null,null,18,"ActivityDto","FINAL","releaseCreated",null,"p00"]
[386,"INFO","2020-02-03T17:32:26",null,null,18,"ActivityDto","FINAL","applicationAssignedToRelease",null,"p00"]

{"sheet":"Update","index":27,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Release Inputs","index":28,"n_rows":22,"n_cols":3,"rows_kept":22,"cut":false,"hidden":true,"merged":[]}
[null,"Column Labels"]
[null,"(blank)","Grand Total"]
["Count of Status",{"$error":"#DIV/0!"},{"$error":"#DIV/0!"}]
[]
[]
[]
[]
["Status","(Multiple Items)"]
[]
[null,"Column Labels"]
[null,"Grand Total"]
["Count of Status",{"$error":"#DIV/0!"}]
[]
[]
[]
[]
[]
["Status","(Multiple Items)"]
[]
[null,"Column Labels"]
[null,"Grand Total"]
["Count of Status",{"$error":"#DIV/0!"}]

{"sheet":"Release Progress","index":29,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"PivotTable","index":30,"n_rows":15,"n_cols":11,"rows_kept":15,"cut":false,"hidden":true,"merged":[]}
[]
[]
["Row Labels",null,null,null,null,null,"Count of Phase Name",null,null,null,"Row Labels"]
["Grand Total",null,null,null,null,null,null,null,null,null,"Grand Total"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,"Row Labels"]
[null,null,null,"Grand Total"]

{"sheet":"PivotChart","index":31,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}